Development of a Low-Cost Paper-

Based Electrochemical Biosensor for

Rapid Dengue NS1 Antigen

Detection

BY: Kanza Touqeer

ID:CA/DF1/184641

Task 3: Project Proposal — CodeAlpha Biotechnology Internship

# Introduction

Dengue fever is one of the most widespread mosquito-borne viral diseases in the world, with the World Health Organization estimating that hundreds of millions of infections occur every year, concentrated heavily in tropical and subtropical regions, including South Asia. Early and accurate diagnosis is critical: dengue can progress from a mild fever to severe, life-threatening hemorrhagic complications within days, and clinical outcomes improve significantly when patients are identified and monitored early in the infection.

The most reliable early biomarker for active dengue infection is the non-structural protein 1 (NS1) antigen, which appears in the blood from the first day of fever and remains detectable for about a week. Current diagnostic options for NS1 fall into two broad categories: laboratory-based enzyme-linked immunosorbent assays (ELISA), which are accurate but require trained personnel, expensive equipment, and centralized laboratories; and rapid lateral-flow immunochromatographic strips, which are fast and simple but generally less sensitive, particularly at low antigen concentrations early in infection.

This proposal outlines a mini-project to design and prototype a low-cost, paper-based electrochemical biosensor for NS1 antigen detection. By combining the affordability and portability of paper-based diagnostics with the sensitivity of electrochemical detection, this project aims to explore a middle path between expensive laboratory testing and less sensitive rapid strip tests, particularly suited to under-resourced clinics and community health centers.

# Problem Statement

In many parts of the world where dengue is endemic, including much of Pakistan and other South Asian countries, healthcare infrastructure is unevenly distributed. Urban tertiary care hospitals may have access to ELISA-based testing, but rural and peri-urban clinics typically rely on rapid antigen strips or must send samples to distant central laboratories, delaying diagnosis by a day or more during outbreak periods when laboratories are overwhelmed.

This gap creates a specific, addressable problem: there is no widely deployed diagnostic tool that is simultaneously (a) inexpensive enough for mass use in low-resource settings, (b) sensitive enough to detect NS1 antigen early in infection, and (c) simple enough to be operated without extensive laboratory training. Recent peer-reviewed research has demonstrated that electrochemical biosensors modified with antibodies, aptamers, or peptides can detect NS1 antigen at concentrations well below 1 nanogram per milliliter, a sensitivity level competitive with laboratory ELISA, while using inexpensive screen-printed or paper-based electrodes. However, most of this research remains at the laboratory prototype stage and has not been translated into an accessible, field-deployable format appropriate for community clinics.

This project addresses that translational gap by proposing a specific, buildable prototype: a disposable, credit-cardsized paper electrode strip, read by a small portable potentiostat device, designed for use by a nurse or lab technician with minimal training and at a materials cost low enough for routine screening during outbreak seasons.

# Objectives

- To design a paper-based electrochemical electrode strip using low-cost, printable conductive materials suitable for detecting the dengue NS1 antigen.

- To functionalize the working electrode surface with a biorecognition element (antibody or aptamer) that selectively binds NS1 antigen with high specificity.

- To evaluate the sensitivity and limit of detection (LOD) of the prototype biosensor using NS1 antigen spiked into buffer and simulated serum samples.

- To compare the performance, cost, and turnaround time of the proposed biosensor against existing ELISA and rapid strip test methods.

- To estimate a realistic per-unit production cost for the biosensor strip to assess its feasibility for large-scale, low-resource deployment.

# Methodology

The project will proceed through five phases over an estimated 10–12 week timeline, moving from materials selection through prototype fabrication, functionalization, testing, and evaluation.

## Phase 1: Materials Selection and Electrode Fabrication (Weeks 1–2)

- Select chromatography-grade paper or filter paper as the substrate, given its low cost, availability, and compatibility with printed conductive inks.

- Fabricate a three-electrode system (working, counter, and reference electrodes) directly on the paper substrate using screen-printing or wax-printing techniques with carbon and silver/silver-chloride conductive inks.

- Test the basic electrical conductivity and reproducibility of the printed electrodes using standard electrochemical techniques such as cyclic voltammetry (CV) with a known redox probe (e.g., potassium ferricyanide).

## Phase 2: Biorecognition Layer Immobilization (Weeks 3–4)

- Functionalize the working electrode surface with a monoclonal anti-NS1 antibody or a DNA/RNA aptamer selected for NS1 binding affinity, following surface modification protocols reported in recent literature (e.g., gold nanoparticle or self-assembled monolayer approaches).

- Introduce a blocking agent (such as bovine serum albumin) to minimize non-specific binding and reduce false-positive signals.

- Confirm successful immobilization using electrochemical impedance spectroscopy (EIS), which detects changes in electron transfer resistance as biomolecules attach to the electrode surface.

## Phase 3: Sensitivity and Specificity Testing (Weeks 5–7)

- Prepare a dilution series of purified or recombinant NS1 antigen in phosphate-buffered saline (PBS), spanning concentrations from approximately 0.1 ng/mL to 1,000 ng/mL, informed by clinically relevant NS1 ranges reported in prior studies.

- Measure the electrochemical response (via differential pulse voltammetry or EIS) at each concentration to construct a calibration curve and determine the limit of detection (LOD) and dynamic range of the sensor.

- Test specificity by exposing the sensor to structurally similar antigens (e.g., Zika virus NS1) to confirm minimal cross-reactivity, and repeat key measurements in a serum-like matrix to approximate real clinical samples.

## Phase 4: Prototype Integration and Usability Testing (Weeks 8–9)

- Pair the paper electrode strip with a compact, low-cost portable potentiostat (or an open-source Arduinobased electrochemical reader) to simulate a field-ready point-of-care device.

- Evaluate the practicality of the full sample-to-result workflow, including sample application volume, reaction/incubation time, and total time to result, aiming for a result within 15–20 minutes.

- Document a simple standard operating procedure that a trained nurse or lab technician, without specialized biochemistry training, could follow.

## Phase 5: Cost Analysis and Comparative Evaluation (Weeks 10–12)

- Calculate the estimated per-strip material cost (paper substrate, conductive inks, antibody/aptamer reagent, blocking agent) and compare it to the market price of existing ELISA kits and rapid antigen strips.

- Summarize sensitivity, specificity, turnaround time, and cost in a comparative table against ELISA and lateral-flow strip methods.

- Identify the key remaining steps needed before the prototype could move toward clinical validation, such as testing on confirmed patient serum samples and regulatory approval pathways.

# Expected Outcome

- A working laboratory prototype of a paper-based electrochemical biosensor capable of detecting NS1 antigen at concentrations in the low nanogram-per-milliliter range, informed by and consistent with sensitivity levels reported in recent peer-reviewed studies.

- A documented, reproducible fabrication and functionalization protocol that could be handed off to further development or academic research groups.

- A comparative cost and performance analysis showing whether the proposed biosensor can meaningfully undercut the cost of ELISA testing while remaining more sensitive than standard rapid antigen strips.

- A clear picture of the remaining technical and regulatory steps required to move the prototype from a laboratory proof of concept toward field deployment in low-resource clinical settings.

- A foundation that could be extended in future work to detect other endemic disease biomarkers (e.g., typhoid, chikungunya) using the same low-cost paper-electrode platform.

# Conclusion

This mini-project proposes a focused, achievable path toward a genuinely useful diagnostic tool: a paper-based electrochemical biosensor that narrows the long-standing gap between expensive, accurate laboratory testing and cheap, less sensitive rapid strips. By building directly on techniques already validated in recent biosensor research and combining them into a single low-cost, field-usable prototype, this project offers both a meaningful learning experience in applied biotechnology and a design that has plausible real-world relevance for dengue-endemic regions with limited healthcare infrastructure.

# References

Bachour Junior, B., Batistuti Sawazaki, M. R., Rocha, R. E. F., Guidelli, É. J., & Mulato, M. (2025). Low-cost labelfree electrochemical aptasensor for dual detection of dengue and Zika using fluorine-doped tin oxide modified with APTES and gold nanoparticles. ACS Omega. https://doi.org/10.1021/acsomega.5c08082

Ferreira, F. F., et al. (2025). Ultrasensitive peptide-based electrochemical biosensor for universal diagnostic of dengue. Biosensors, 15(4), 236. https://doi.org/10.3390/bios15040236

Kumar, A., & colleagues. (2020). Polyaniline based electrochemical sensor for the detection of dengue virus infection. PMC. https://pmc.ncbi.nlm.nih.gov/articles/PMC7229450/

Nasrin, F., et al. (2015). Quantification of NS1 dengue biomarker in serum via optomagnetic nanocluster detection. Scientific Reports, 5, 16145. https://doi.org/10.1038/srep16145

Shahrtash, S. A., Ghnim, Z. S., Ghaheri, M., Adabi, J., Hassanzadeh, M. A., Yasamineh, S., Afkhami, H., Kheirkhah, A. H., Gholizadeh, O., & Moghadam, H. Z. (2025). Recent advances in the role of different nanoparticles in the various biosensors for the detection of the chikungunya virus. Molecular Biotechnology, 67(1), 54–79. https://doi.org/10.1007/s12033-024-01052-6

World Health Organization. (2024). Dengue and severe dengue: Key facts. https://www.who.int/news-room/factsheets/detail/dengue-and-severe-dengue